## Sheet1
Implementation Schedule & Budget for Catalysing Co-Management - Three Year Programme Overview
WWF Project KE0087: Conservation and Development of Kiunga Marine National Reserve, Kenya
Currency: USD
Phasing of implementation indicated by expenditure per period
Result | Activity | Method or Resource | Year 1 | Year 2 | Year 3
1. Creation of CMB | Literature review and interviews | Consultant | 1200 | 0 | 0
| Introductory stakeholder dialogue | Workshops: facilitator | 3300 | 0 | 0
| Vision, Objectives, Co-Management Prog. | Workshops: facilitator | 3300 | 0 | 0
| Community mobilisation - elected reps. | KMNR outreach | 2500 | 500 | 500
| CMB Constitution, Procedures, Links | CMB internal/legal | 2500 | 0 | 0
| Partner MOUs | CMB internal/legal | 2500 | 0 | 0
| Trust Fund establishment and admin | CMB/legal/financial | 2500 | 500 | 500
| Documentation | Facilitator | 1000 | 400 | 400
| Publicity | CMB/WWF | 2000 | 500 | 500
| Lobbying | CMB/WWF - consultations | 3000 | 500 | 500
| Information sharing | CMB/WWF | 1000 | 1000 | 1000
|  | Travel - flights | 4500 | 0 | 0
|  | Travel - boats | 3500 | 4500 | 4500
|  | Travel - car | 2000 | 1000 | 1000
|  | Stationery | 3000 | 1000 | 1000
|  | Food & Accommodation | 2600 | 2000 | 2000
|  |  | 40400 | 11900 | 11900
2. Co-Management Strategy | Integration of CMB in KMNR Mgt. Plan | CMB/WWF/Facilitator | 3300 | 0 | 0
|  |  | 3300 | 0 | 0
3. Annual Operating Plans | Annual planning relative to CMB strategy | CMB | 1500 | 1000 | 1000
|  |  | 1500 | 1000 | 1000
4. CMB oversees Joint Venture | Ecotourism potential assessment | Tourism economist | 3500 | 0 | 0
Partnerships (JVPs) | Ecotourism development planning | Planner/ecologist | 9500 | 1000 | 0
in Eco-tourism | Clarify tenure status | CMB/WWF/legal/GoK | 3000 | 2500 | 0
| Decide terms of JVPs | CMB/WWF/Facilitator | 2000 | 0 | 1000
| Decide terms of tender process | CMB/WWF/Facilitator | 1000 | 0 | 0
| Invitation to tender | CMB/WWF - press | 500 | 500 | 500
| Evaluation of proposals | CMB/WWF/Facilitator | 2000 | 1500 | 0
| Finalise Joint Venture Agreements | CMB/WWF/Facilitator/legal | 3000 | 0 | 1000
| Commence tourism operations | JVP/CMB | 0 | 0 | 0
| Publicity | CMB/WWF | 2000 | 500 | 500
|  | Travel - flights and surveys | 8000 | 2000 | 2000
|  | Travel - boats | 6000 | 4500 | 4500
|  | Travel - car | 4500 | 2000 | 1000
|  | Stationery | 4500 | 2000 | 2000
|  | Satellite imagery | 2000 | 0 | 1000
|  | Food & Accommodation | 2400 | 2000 | 2000
|  |  | 53900 | 18500 | 15500
5. CMB establishes Certified | Business Plan | Fisheries Economist | 8000 | 2000
Sustainable Lobster & Crab | Sustainability Analysis | Fisheries Ecologist | 8000 | 5000 | 5000
Fishery | Awareness raising and mobilisation | KMNR outreach | 5000 | 3000 | 3000
| Clarify resource tenure status | CMB/WWF/legal/GoK/FiD | 1500 | 500 | 0
| Lobbying | CMB/WWF - consultations | 1500 | 3000 | 500
| Fisher Assocn. Constitution; Membership | CMB/WWF/Fishers/Facilitator | 0 | 3000 | 0
| By-laws deliberations | CMB/WWF/Fishers/Facilitator | 0 | 3000 | 0
| Compliance monitoring | CMB/WWF/Fishers/Facilitator | 0 | 5000 | 5000
| Fisher training | CMB/WWF/Fishers/Facilitator | 0 | 3000 | 3000
| Lobster facility staff training | CMB/WWF/Fishers/Facilitator | 0 | 2000 | 2000
| Facilities development - cold storage, etc. | CMB/WWF/Fishers/Facilitator | 0 | 35000 | 3500
| Marketing and promotion | CMB/WWF | 3000 | 5000 | 5000
| Publicity | CMB/WWF | 500 | 2000 | 1000
|  | Travel - flights | 6000 | 0 | 0
|  | Travel - boats and surveys | 10000 | 0 | 0
|  | Travel - car | 2000 | 1000 | 1000
|  | Stationery | 2500 | 1000 | 1000
|  | Food & Accommodation | 2400 | 2000 | 2000
|  |  | 50400 | 75500 | 32000
6. CMB develops commercial | Research, monitoring, training assessment | Consultant | 2000 | 3000 | 0
relationships with academic | Research potential partners | CMB/WWF - internet, etc. | 1500 | 2000 | 0
sector | Review precedents; check market rates | CMB/WWF | 0 | 2000 | 0
| Exchange visits (subsidised by universities) | CMB/KMNR | 2000 | 9000 | 0
| Site selection surveys | CMB/KWS | 0 | 5000 | 0
| Tenure status/dispensations negotiated | CMB/WWF/legal/GoK | 0 | 3000 | 0
| Solicit expressions of interest | CMB | 0 | 500 | 0
| Refine terms of cooperation | CMB/WWF/legal/Govt. | 0 | 1500 | 500
| Decide terms of tender process | CMB/Facilitator | 0 | 1000 | 0
| Invitation to tender | CMB/WWF - press | 0 | 0 | 500
| Evaluation of proposals - select partner/s | CMB/Facilitator | 0 | 0 | 2000
| Finalise Joint Venture Agreements | CMB/WWF/Consultant/legal | 0 | 0 | 3000
| Commence operations | JVP/CMB | 0 | 0 | 0
| Publicity | CMB/WWF | 0 | 2000 | 2000
|  | Travel - flights | 1500 | 6500 | 0
|  | Travel - boats | 1000 | 3000 | 2500
|  | Travel - car | 900 | 0 | 1000
|  | Stationery | 1000 | 1000 | 1000
|  | Food & Accommodation | 600 | 2000 | 2000
|  |  | 10500 | 41500 | 14500
7. Monitoring & Evaluation undertaken | Annual tech and financial tracking | Audit and Tech team reviews | 4000 | 4000 | 2500
| Three year evaluation | Review team |  |  | 9000
|  | Travel - flights | 2000 | 2000 | 3500
|  | Travel - boats | 1800 | 1800 | 3000
|  | Travel - car | 800 | 800 | 1000
|  | Stationery & Comms | 1000 | 1000 | 1000
|  | Food & Accommodation | 0 | 0 | 2000
|  |  | 9600 | 9600 | 22000
| Subtotal 1 | TOTAL COSTS | 169600 | 157000 | 96900
8. Internal costs recovery |  |  | 25440 | 23550 | 14535
| Final Total | TOTAL COSTS | 195040 | 180550 | 111435