## Sheet1
Implementation Schedule & Budget: Co-Management of Dodori-Boni, Kenya
WWF Project KE0087: Conservation and Development of the Kiunga Marine & Dodori National Reserves, Kenya
Currency: USD
Phasing of implementation indicated by expenditure per period
Budget Summary
Result
| Year 1 | Year 2 | Total
1:Co-Management Board | 43500 | 10400 | 53900
2: Landscape Assessment | 38800 | 1000 | 39800
3: General Management Plan | 57100 | 3300 | 60400
4: Improved KWS capacity | 270950 | 5500 | 276450
5: Annual operations plan | 3000 | 3000 | 6000
6: Ecotourism development plan | 17700 | 0 | 17700
7: Ecotourism joint ventures | 13500 | 12000 | 25500
7: Monitoring & Evaluation | 12000 | 15000 | 27000
| 456550 | 50200 | 506750
Implementation Schedule & Budget: Co-Management of Dodori-Boni, Kenya
WWF Project KE0087: Conservation and Development of the Kiunga Marine & Dodori National Reserves, Kenya
Currency: USD
Phasing of implementation indicated by expenditure per period
Result | Activity | Method or Resource | Year 1 | Year 2
1:Co-Management Board | Literature review and interviews | Consultant | 2500 | 0
| Introductory stakeholder dialogue | Workshops: facilitator | 2000 | 0
| Vision, Objectives | Workshops: facilitator | 2500 | 0
| Community mobilisation - elected reps. | WWF outreach | 3000 | 500
| CMB Constitution, Procedures, Links | CMB internal/legal/WWF | 2500 | 0
| Partner MOUs | CMB internal/legal/WWF | 2500 | 0
| Trust Fund establishment and admin | CMB/legal/financial/WWF | 2500 | 500
| Documentation | Facilitator/WWF | 1000 | 400
| Publicity | CMB/WWF | 2000 | 1000
| Lobbying | CMB/WWF - consultations | 3000 | 1000
| Information sharing | CMB/WWF | 1000 | 1000
|  | Travel - flights | 7000 | 0
|  | Travel - boats | 1500 | 500
|  | Travel - car | 5000 | 3000
|  | Stationery | 3000 | 1000
|  | Food & Accommodation | 2500 | 1500
|  |  | 43500 | 10400
2: Landscape Assessment | Desk research: Nairobi, Lamu | Ecologist/Planner | 3000 | 0
| Interviews Lamu, Garissa, Nairobi. | Ecologist/Planner | 2500 | 0
| Aerial survey - ecosystem | Ecologist/Planner | 2000 | 0
| Satellite imagery time series analysis | Ecologist/Planner | 3000 | 0
| Ground survey – car/foot/boat | Ecologist/Planner/Soil Scientist | 3000 | 0
| PRA – local farmers – trad. knowledge | Ecologist/Planner/Soil Scientist | 2500 | 0
| Awareness raising | WWF outreach | 1000 | 0
| Map production | Ecologist/Planner | 1500 | 0
| Draft Report | Ecologist/Planner | 2500 | 0
| CMB input | Ecologist/Planner/CMB/WWF | 1000 | 0
| Final Report | Ecologist/Planner | 2000 | 0
| Publicity | CMB/WWF | 1000 | 0
| Lobbying | CMB/WWF - consultations | 1000 | 1000
| Information sharing | CMB/WWF | 1000 | 0
|  | Film and processing | 300 | 0
|  | Comms | 500 | 0
|  | Repro | 1000 | 0
|  | Survey flight | 1500 | 0
|  | Travel - flights | 3000 | 0
|  | Travel - boats | 500 | 0
|  | Travel - car | 1500 | 0
|  | Stationery | 1000 | 0
|  | Food & Accommodation | 2500 | 0
|  |  | 38800 | 1000
3: General Management Plan | Orientation and Initiation - scope of work | Ecologist/Planner/CMB/KWS HQ | 1500 | 0
| Desk research: Nairobi, Lamu, Garissa | Ecologist/Planner | 3000 | 0
| Interviews Lamu, Kiunga, Garissa, Nairobi. | Ecologist/Planner | 2500 | 0
| Awareness raising | WWF outreach | 1000 | 0
| Aerial survey DNR | Ecologist/Planner | 2000 | 0
| Satellite imagery time series analysis | Ecologist/Planner | 500 | 0
| Ground survey – car/foot/boat - DNR | Ecologist/Planner/CMB | 5000 | 0
| PRA resource users | Ecologist/Planner/CMB | 1500 | 0
| Private sector consultation | Ecologist/Planner | 500 | 0
| Map production | Ecologist/Planner | 2000 | 0
| Documentation | Ecologist/Planner | 600 | 0
| Pre-plan workshop preparation | Ecologist/Planner/CMB/Facilitator | 550 | 0
| Pre-plan workshop - Purpose, Issues | Ecologist/Planner/CMB/Facilitator | 2000 | 0
| Documentation and Feedback | Ecologist/Planner/Facilitator | 1000 | 0
| Plan generation workshop preparation | Ecologist/Planner/CMB/Facilitator | 550 | 0
| Plan generation workshop | Ecologist/Planner/CMB/Facilitator | 5000 | 0
| Draft Plan | Ecologist/Planner | 2000 | 0
| CMB review Draft and suggest revisions | Ecologist/Planner/CMB/WWF | 1000 | 0
| Draft Revised re CMB input | Ecologist/Planner | 2000 | 0
| KWS Board review Draft | KWS HQ | 0 | 0
| Draft Revised re KWS Board input | Ecologist/Planner | 400 | 0
| Final Plan approved by KWS Board | KWS HQ | 0 | 0
| CMS review and Annex | CMB/Facilitator |  | 1000
| Publicity | CMB/WWF | 1000
| Lobbying | CMB/WWF - consultations | 1000 | 0
| Information sharing | CMB/WWF | 1000 | 0
|  | Film and processing | 500 | 0
|  | Comms | 1000 | 0
|  | DTP and Repro | 2000 | 0
|  | Survey flight | 2500 | 0
|  | Travel - flights | 4000 | 500
|  | Travel - boats | 500 | 500
|  | Travel - car | 4000 | 500
|  | Stationery | 1000 | 500
|  | Food & Accommodation | 4000 | 300
|  |  | 57100 | 3300
4: Improved KWS capacity
CAPITAL
Outposts - one each DNR/BNFR | Survey - site selection | CMB/KWS KMNR | 1000
Semi-permanent/rustic design | Site development plan | CMB/Landscape architect | 2000
Patrols from outposts use fly camps | Materials - cement, blocks, poles, thatch | WWF/KWS HQ/KWS KMNR | 25000
| Materials - WC Fittings, septic tanks | WWF/KWS HQ/KWS KMNR | 6000
| Labour costs | WWF/KWS HQ/KWS KMNR | 6000
| Transport costs | WWF/KWS HQ/KWS KMNR | 5000
|  |  | 45000 | 0
Communications system | HF Radio base station, repeater | WWF/KWS HQ/KWS KMNR | 2500
| VHF base station, handhelds | WWF/KWS HQ/KWS KMNR | 2500
|  |  | 5000 | 0
Power | Portable generator | WWF/KWS HQ/KWS KMNR | 500
| Solar power system | WWF/KWS HQ/KWS KMNR | 2000
|  |  | 2500 | 0
Water | Wellpoint | WWF/KWS HQ/KWS KMNR | 3000
| Pump | WWF/KWS HQ/KWS KMNR | 600
| Storage tank and stand | WWF/KWS HQ/KWS KMNR | 600
| Reticulation | WWF/KWS HQ/KWS KMNR | 500
|  |  | 4700 | 0
Roads and tracks | Bulldozer; graded two blades-width | WWF/KWS HQ/KWS KMNR | 50000
Boundary demarcation | Bulldozer; graded one blade-width | WWF/KWS HQ/KWS KMNR | 60000
Airstrip | Bulldozer; graded 1000m x 16m | WWF/KWS HQ/KWS KMNR | 30000
| Airstrip - markers and wind sock | WWF/KWS HQ/KWS KMNR | 1000
|  |  | 141000 | 0
Transport | Toyota Land Cruiser p/up. 4.5 petrol | WWF/KWS HQ/KWS KMNR | 70000
|  |  | 70000 | 0
RECURRENT
Training | Wildlife monitoring; multiple use; etc | CMB/KWS | 1000 | 2000
Maintenance |  | CMB/KWS | 250 | 2000
Ranger elephant monitoring work |  | CMB/KWS | 500 | 1000
KWS counterpart field allowance |  | CMB/KWS | 500 | 500
Sustainability: co-financing plan |  | CMB/KWS/Facilitator | 500 | 0
|  |  | 2750 | 5500
5: Annual operations plan |  | CMB Partners/WWF/Facilitator | 3000 | 3000
|  |  | 3000 | 3000
6: Ecotourism development plan | Desk research | Ecologist/Planner | 1000 | 0
| Market and private sector research | Ecologist/Planner | 1000 | 0
| Aerial survey DNR | Ecologist/Planner/CMB | 300 | 0
| Site survey - ground DNR | Ecologist/Planner/CMB | 2000 | 0
| EIA | Ecologist/Planner | 1000 | 0
| Draft Plan | Ecologist/Planner | 1000 | 0
| Presentation to CMB | Ecologist/Planner/CMB | 500 | 0
| Final Report | Ecologist/Planner | 600 | 0
| Publicity | CMB/WWF | 500 | 0
| Lobbying | CMB/WWF - consultations | 500 | 0
| Information sharing | CMB/WWF | 500 | 0
|  | Film and processing | 200 | 0
|  | Comms | 300 | 0
|  | DTP and Repro | 1000 | 0
|  | Survey flight | 1500 | 0
|  | Travel - flights | 500 | 0
|  | Travel - boats | 500 | 0
|  | Travel - car | 500 | 0
|  | Stationery | 300 | 0
|  | Food & Accommodation | 4000 | 0
|  |  | 17700 | 0
7: Ecotourism joint ventures | Ecotourism potential assessment | Business Analyst/Economist | 2000 | 0
| Clarify tenure status | CMB/WWF/legal/GoK | 3000 | 500
| Decide terms of JVPs | CMB/WWF/Consultant | 2000 | 0
| Decide terms of tender process | CMB/WWF/Consultant | 1000 | 0
| Invitation to tender | CMB/WWF - press | 0 | 500
| Evaluation of proposals | CMB/WWF/Consultant | 0 | 2000
| Finalise Joint Venture Agreements | CMB/WWF/Consultant/legal | 0 | 3000
| Commence tourism operations | JVP/CMB | 0 | 0
| Publicity | CMB/WWF |  | 2000
|  | Travel - flights and surveys | 2500 | 0
|  | Travel - boats | 1000 | 0
|  | Travel - car | 500 | 1000
|  | Stationery | 500 | 1000
|  | Satellite imagery | 0 | 0
|  | Food & Accommodation | 1000 | 2000
|  |  | 13500 | 12000
8: Monitoring & Evaluation | Inception report | Consultant | 2000
| Mid-term review | Consultant | 10000
| Review and evluation | Consultant |  | 15000
|  |  | 12000 | 15000